## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2191-swen-261-05-b-Ages6ToAdult
Instructions | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | Joey Trumbull
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | Joey Trumbull
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | Joey Trumbull
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | Joey Trumbull
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | Joey Trumbull
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | Joey Trumbull
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | Joey Trumbull
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | Lacey Dallum
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | Lacey Dallum
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | Lacey Dallum
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | Lacey Dallum
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | Lacey Dallum
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | Lacey Dallum
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | Lacey Dallum
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | Lacey Dallum
Epic: Movement
As a user, I want to be able to move pieces forward so that I can get closer to my opponents and continue the game. | Given that when it is my turn, when I click a piece, I must be able to drag the piece to a valid move
Given that it is not my turn, when I drag a piece, then the move must be rejected
Given that it is my turn, when I drag a piece to an invalid position, then the move must be rejected
Given that I am trying to move a regular piece, when I try to make a move, then only valid moves to the front diagonal of the piece should be accepted
Given that I am trying to move a king, when I try to make a move, then only valid moves to the front and back diagonals of the piece should be accepted.
Given that I am trying to move, when there is a valid jump that can be made, any moves not including a jump must be rejected
As a user, I want to be able to jump my opponents so that I can capture their pieces and (potentially) win the game. | Given that it is my turn, when I click on a piece, then I must be able to move/jump with the piece
Given that it is my turn, when I try to move a piece without jumping it and a jump is available, then the move must be rejected.
Given that it is my turn, when I try to make an available jump, then it will move the piece and take the jumped player's piece.
Given that it is my turn, if there is a multiple jump available, then I must be able to jump more than one piece eliminating it from the board.
Given that it is my turn, if I make an invalid jump, then the move must be rejected.
As a user, I want to be able to crown my Checkers piece so I can move forwards and backwards. | Given that a piece is not a king already, when I move the piece to the opposing side's final row, then my piece will be crowned
Given that the piece is now a king, the sprite must change showing a crowned king
As a user, I want to be able to sign-out so I can sign-in to my account from a different device | Given that I have not signed out, when I want to sign out, then there will be an option that is always available for me to sign out of my account.
Given that I am signed in, when I sign out, my account will be logged out and my screen will change to the main menu screen regardless of whether I'm in a game or not (this will cause a resignation)
Given that I have signed out, when a player looks on the home page, then they will not see my username under the player lobby.
As a user, I want to be able to forfeit any game so that I can quit playing the current game I'm in. | Given that I am in the game when I see the game page then I must see a means to resign.
Given that I have not resigned, when I click on resign, then I must be redirected back to the home page
Given that I have resigned, when I move back to the home page, then I must see a message stating my resignation.
Given that I am in a game, when my opponent resigns, then it must give me a notification that I won because of resignation and bring me back to the home page.
As a user, I want to be able to view players statistics so that I know how I rank compared to them. | Given that I am signed in, when I look at my profile, then there must be a number of wins/losses that have been tracked and displayed.
Given that I am signed in, when I look at another person from the PlayerLobby, I must see their wins and losses displayed.
Given that I win a game, when I leave, there must be a new win that has been recorded.
Given that I lose a game, when I leave, there must be a new loss that has been recorded.
As a user, I want to be able to enter tournaments so that I can play ranked games that affect my player statistics. | Given that I am signed in and not playing a game, when I look at the main menu, then there must be an option to start a tournament.
Given that I am not playing a game, when I click the tournament button, then I must be entered in a queue that waits for others to join.
Given that others have not joined, when I try to enter a new game or tournament, then nothing must happen.
Given that I am still signed in, when the queue fills up, then a new tournament starts
Given that I have been queued for a tournament, when I log out, then I will be resigned from my matches
Given that I have not resigned or lost, when I win a game, then I must be able to play against other people who have won all of their games as well or win the tournament
Given that I have not resigned or lost, when I lose a game, the I must be exited from the tournament queue and returned to the main menu.